## Slide 1
TEAM ALIGNMENT
IFC Preparation
如何编制 IFC 发包文件包
Gelephu Airport (GLU) · Structuring the Issued-For-Construction Package
APMT / PMO · Project Management Office
Package → Asset/Zone → Discipline/System → Document Type → Number → Revision/Status
STRICTLY CONFIDENTIAL
1

## Slide 2
目录 Contents
本次对齐覆盖 IFC 的组织原则、工程包矩阵、卷册结构、登记册、编码与发布门槛
01
组织原则与工程包 Principle & Packages
▸ Slide 3 — 为什么要现在统一 Why align now
▸ Slide 4 — IFC 组织原则 Organising principle
▸ Slide 5 — 工程包矩阵 IFC-00~08 Package matrix
02
结构与控制工具 Structure & Controls
▸ Slide 6 — 卷册结构 Volume 0~8 Volume structure
▸ Slide 7 — 图纸/规范登记册 Master register
▸ Slide 8 — 关键接口与 Hold Points
03
编码标准 Coding Standards
▸ Slide 9 — 图号编码 Drawing coding
▸ Slide 10 — 规范编码 Specification coding
▸ Slide 11 — IFC 发布检查清单 Issue checklist
04
职责与下一步 Roles & Next Steps
▸ Slide 12 — 牵头责任 Lead ownership
▸ Slide 13 — 工作流程 CDE workflow
▸ Slide 14 — 下一步行动 Next steps
STRICTLY CONFIDENTIAL
2

## Slide 3
为什么现在统一 Why Align Now
在第一份 IFC 冻结之前统一规则 — 否则各专业各包各自编号，后期无法控制
1
一个不可控的图纸清单是最大风险
If PTB, airfield, landside, airport systems and authority/interface items are mixed into one uncontrolled drawing list, FIDIC administration, tender evaluation and claims management all break down.
2
IFC 直接服务于合同与施工监理
The IFC package feeds FIDIC administration, tender evaluation, contract award, construction supervision and future claims — it must be navigable by package, discipline and document type.
3
GLU 已有 PMO 数据室与命名规则
WIP / Issued / Submission / Milestone Review folders already exist, with naming by date, project, originator, role, content and revision. IFC must build on this, not replace it.
4
图号必须稳定，独立于文件名
File names change with issue date; the IFC drawing/spec NUMBER must stay stable so the contractual baseline can be tracked through revisions.
5
本次对齐的产出
One agreed organising principle, the IFC-00~08 package matrix, the Volume 0~8 structure, the master register fields, drawing & spec coding, and the IFC issue gate checklist.
STRICTLY CONFIDENTIAL
3

## Slide 4
IFC 组织原则 Organising Principle
先按合同包，再按专业/系统，最后按文档类型 — 这是整个 IFC 的骨架
Package
合同包
IFC-00 ~ IFC-08
›
Asset / Zone
资产/区域
Runway · PTB · RCL · Fuel Farm
›
Discipline /
System
专业/系统
AR · ST · CV · AGL · BHS · SEC
›
Document Type
文档类型
Drawing · Spec · Schedule · Model
›
Number
编号
Stable, date-independent
›
Revision /
Status
版本/状态
IFC · Superseded · As-Built
示例 Worked example
GLU-P02-PTB-AR-PLN-0101 = Package 2 PTB · Architecture · Plan · drawing 0101
原则收益 Why it works：避免把 PTB、机场跑道、陆侧、机场系统和当局/接口事项混入同一份不可控清单；每一份文件都能定位到包、资产、专业、类型与版本，便于 FIDIC 管理、评标、授标与索赔管理。
STRICTLY CONFIDENTIAL
4

## Slide 5
IFC 工程包矩阵 Package Matrix
九个 IFC 包 — 每个包都有明确的主范围、关键专业、接口/Hold Points 与牵头责任方
Package
Main Scope / Key Disciplines
Key Interface / Hold Points
Lead Owner
IFC-00
General / Common Requirements
Contract order · registers · interface matrix · RFI/TQ
APMT / PMO / QS
IFC-01
Airfield & Integrated Building
PTB · airspace · DoAT · BCAA · flight calibration · certification
CAPE / APMT
IFC-02
PTB & Landside Main Works
Apron · PBB · security · Customs · Immigration · airlines · municipal
BIG / Aurecon / CAPE
IFC-03
PTB Annex / Support Buildings
PTB · back-of-house · goods & waste flow · utilities
D103i / Aurecon / APMT
IFC-04
GA Terminal / Royal Ceremonial Lounge
PTB · apron · VVIP route · Immigration · MoFA / protocol
BIG / CAPE / Aurecon
IFC-05
Landside Landscape / Plaza / Canopy
PTB entrances · roads · public realm · accessibility
BIG / Aurecon
IFC-06
Specialist Airport Systems / NSC
FAT/SAT/T&C · O&M · spares · cross-system interfaces
CAPE / APMT / Specialists
IFC-07
Third-Party / Operator Facilities
Druk Air · BOC · DoAT · NCHM · future operator agreements
APMT / CAPE / 3rd Parties
IFC-08
Reference / Information Only
Must be marked 'For Information Only' unless a Contract Document
APMT / PMO
STRICTLY CONFIDENTIAL
5

## Slide 6
卷册结构 Document Volume Structure
每个 IFC 包采用同一卷册逻辑 (Volume 0~8)，PM/CS 与承包商可一致导航
V0
IFC Master Register
唯一受控登记册：列出 IFC 基线中的每一份图纸、规范、报告、模型与参考文件
V1
Governing / Contract Docs
Conditions of Contract · Particular Conditions · contract data · forms · clarifications & addenda
V2
Technical Specifications
按包、专业、系统组织的全部技术规范
V3
BoQ / Pricing Schedules
BoQ · schedules of rates · provisional sums · PC items · measurement rules
V4
Drawings
按包、资产、专业、图纸类型分组的 IFC 图纸
V5
Reports / Site Information
SI · geotech · hydrology · ESIA · survey · existing utilities — 区分 'Contractual' vs 'For Info Only'
V6
Project / GMC / Authority
GMC · sustainability · OHS · BIM/CDE · local workforce · authority & aerodrome certification
V7
BIM / Digital Deliverables
IFC models · RVT/NWC/NWD/IFC · clash reports · model status · BEP · BIM QC · handover
V8
Interface & Authority Register
Interface matrix · authority tracker · stakeholder register · RFI/TQ close-out · deviation register
STRICTLY CONFIDENTIAL
6

## Slide 7
图纸与规范登记册 Master Register
APMT 为每个 IFC 包维护的核心控制矩阵 — 这是 IFC 的单一事实来源
Package Code
IFC-01 Airfield, IFC-02 PTB & Landside …
Asset / Zone
Runway, Taxiway, Apron, PTB, RCL, Fuel Farm …
Discipline / System
AR ST CV DR ME EL ICT AGL NAV MET BHS PBB SEC LS BIM
Document Type
Drawing · Spec · Schedule · Report · Model · Calc
Document Number
Stable number — NOT dependent on date
Document Title
Full drawing or specification title
Revision
A/B/C · Rev 0/1 · IFC-A/IFC-B
Status
WIP · For Review · For Tender · IFC · Superseded · As-Built
IFC Baseline Date
Date included in the contractual IFC register
Originator
BIG · AUR · CAPE · CAI · MQD · 360 · D103i
Checker / Approver
Designer checker · APMT reviewer · authority
Related Spec / BoQ
Cross-ref to spec section & BoQ item
Related Model
BIM model file name & revision
Authority Dependency
BCAA · DoAT · MoIT · NCHM · BOC · airlines
Interface Dependency
Airfield–PTB · PBB–Apron · BHS–MEP · ANS–DoAT
Contractual Status
Contract Doc · Ref Only · CDP · Provisional Sum · D&B
Remarks / Open Items
Pending RFI · authority comment · clarification · deviation
STRICTLY CONFIDENTIAL
7

## Slide 8
关键接口与 Hold Points Key Interfaces & Hold Points
跨包接口是 IFC 风险最集中的地方 — 在 V8 接口登记册中逐条登记与跟踪
Airfield ↔ PTB
Apron / PBB / AVDGS geometry, levels and service connections between IFC-01 and IFC-02 must reconcile before either freezes.
PTB ↔ Landside
Plaza, canopy, roads, drainage and utilities (IFC-02/05) tie to municipal road & utilities — confirm boundary of supply.
Systems ↔ Building
BHS–MEP, security screening, ICT containment and power for IFC-06 specialist systems must be coordinated with IFC-02/03.
Authority Hold Points
BCAA / DoAT / NCHM approvals, flight calibration and aerodrome certification gate the airfield & systems packages.
VVIP / Ceremonial
RCL ceremonial route, security, Immigration & Customs (IFC-04) interface with PTB and apron — MoFA / protocol sign-off.
Third-Party Facilities
Fuel farm, ground handling, cargo, catering (IFC-07) need utility, access and apron interfaces fixed with operators.
STRICTLY CONFIDENTIAL
8

## Slide 9
图号编码 Drawing Coding
稳定的图号不随文件名或发布日期改变 — GLU-[Package]-[Asset]-[Discipline]-[Type]-[Sequence]
GLU - [Package] - [Asset] - [Discipline] - [Type] - [Sequence]
示例 Examples
GLU-P01-RWY-CV-PLN-0001
Airfield · Runway · Civil · Plan
GLU-P01-APR-AGL-LAY-0010
Airfield · Apron · AGL · Layout
GLU-P01-IBG-ME-SCH-0020
Integrated Building · Mech · Schedule
GLU-P02-PTB-AR-PLN-0101
PTB · Architecture · Plan
GLU-P02-PTB-ST-DTL-0205
PTB · Structure · Detail
GLU-P02-LDS-CV-PLN-1001
Landside · Civil · Plan
GLU-P04-RCL-AR-SEC-0005
RCL · Architecture · Section
GLU-P06-BHS-SY-DIA-0001
Specialist · BHS · System Diagram
专业代码 Discipline Codes
AR
Architecture
ST
Structure
CV
Civil
DR
Drainage
ME
Mechanical
EL
Electrical
FP
Fire Protection
ICT
ICT / ELV
AGL
Airfield Ground Lighting
NAV
NAVAIDS / ANS
MET
Meteorological
BHS
Baggage / HBS
PBB
Boarding Bridge / AVDGS
SEC
Security / Access
LS
Landscape
BIM
Digital Model
GEN
General / Common
STRICTLY CONFIDENTIAL
9

## Slide 10
规范编码 Specification Coding
以 CSI MasterFormat 为参照，叠加机场专用章节 — 不要把机场系统硬塞进纯建筑分项
CSI MasterFormat (参照 reference)
00
Procurement & contract
01
General · doc control · BIM/CDE · QA/QC · HSE
02
Existing conditions · demolition · utilities diversion
03
Concrete
04
Masonry
05
Metals / structural / green steel
06
Timber / Mass Engineered Timber
07
Roofing · waterproofing · façade
08
Doors · windows · glazing
09
Finishes
10
Signage · wayfinding · specialties
11
Airport & specialist equipment
21
Fire protection
22
Plumbing
23
HVAC
26
Electrical
27
Communications / ICT
28
Security / ELV / CCTV / access
31
Earthworks · ground improvement · slopes
32
Pavement · roads · landscape · external
33
Utilities
机场专用分项 Airport-specific (40-AF ~ 48-OR)
40-AF
Airfield civil works, geometry & pavements
41-AF
Airfield drainage, culverts, river-crossing
42-AF
Airfield markings, signage & visual aids
43-AF
Airfield Ground Lighting & ALCMS
44-AF
NAVAIDS, ANS & airspace infrastructure
45-AF
Meteorological systems
46-AF
ARFF facilities & fire training
47-AS
Airport specialist: BHS/HBS/PBB/AVDGS/PAVA/FIDS/PSS/SACS
48-OR
Testing, commissioning, ORAT, certification & handover
STRICTLY CONFIDENTIAL
10

## Slide 11
IFC 发布检查清单 Minimum IFC Issue Checklist
任何图纸或规范标记为 IFC 之前，团队必须逐项确认 — 全部为强制 Required
✓
列入 IFC 主登记册 In IFC master register
✓
版本明确并已冻结 Revision identified & frozen
✓
设计专业 checker / approver 完成
✓
APMT 审查完成 APMT review completed
✓
关键 RFI / TQ 已关闭或列为待澄清
✓
关联规范已交叉引用 Spec cross-referenced
✓
关联 BoQ / 计价项已交叉引用
✓
BIM 模型版本与图纸发布一致
✓
已检查与其他包的接口 Interface checked
✓
已记录当局/相关方依赖 Authority dependency
✓
承包商设计部分已明确标识 (CDP)
✓
暂定金额/性能规范已明确标识
✓
已标记 'Contract Document' 或 'For Info Only'
✓
被取代文件已移出合同基线 Superseded removed
STRICTLY CONFIDENTIAL
11

## Slide 12
牵头责任 Lead Ownership
每个包都有明确的牵头方 — APMT 统筹登记册、接口矩阵与发布门槛
APMT / PMO
Overall IFC governance · master register (V0) · interface & authority registers (V8) · IFC issue gate
IFC-00 全包统筹
CAPE
Airfield & integrated building · specialist airport systems coordination
IFC-01 · 06 · 07
BIG (Architect)
PTB & landside lead design · GA Terminal / RCL · landscape & plaza
IFC-02 · 04 · 05
Aurecon
Engineering across PTB, annex, RCL, landscape and supporting disciplines
IFC-02 · 03 · 04 · 05
D103i
PTB annex / operational support buildings
IFC-03
QS / Specialists
BoQ & pricing (V3) · specialist system designers for NSC packages
IFC-00 · 06
STRICTLY CONFIDENTIAL
12

## Slide 13
工作流程 CDE Workflow
IFC 建立在 GLU 现有 PMO 数据室之上 — WIP → Issued → Submission → Milestone Review
WIP
进行中
Designer working files · not shared as contractual
›
Issued
已发布
Checked & approved · shared via CDE
›
Submission
提交
Formal submission to APMT / authority
›
Milestone
Review
里程碑审查
Aligned to scope, codes, masterplan, safety, constructability, QA/QC, schedule
沿用现有规则 Build on existing PMO conventions
文件命名按 date · project · originator · role · content · revision；IFC 图号则使用稳定编号 (见 Slide 9)。复用现有 'For Construction Drawing/Models Packages'、材料规范与 BIM 交付框架 (V7)。
里程碑审查门槛 Milestone gate：deliverables 须满足 scope · project goals · international codes · masterplan standards · design safety · constructability · design risk · coordination · QA/QC · schedule — 通过后方可进入 IFC 发布检查清单 (Slide 11)。
STRICTLY CONFIDENTIAL
13

## Slide 14
下一步行动 Next Steps
对齐后两周内启动 — 以 IFC-00 主登记册与编码标准为先
1
锁定组织原则与编码
Confirm Package→Asset→Discipline→Type→Number→Rev as the single principle; freeze drawing & spec coding (Slide 4/9/10).
All / APMT
Week 1
2
建立 IFC 主登记册 (V0)
Stand up the master register with all 17 control fields; one register per package, owned by APMT.
APMT / PMO
Week 1-2
3
填充工程包矩阵
Each lead populates IFC-00~08 scope, disciplines, interfaces and document lists (Slide 5).
CAPE/BIG/Aurecon/D103i
Week 2-3
4
开启接口与当局登记册 (V8)
Log every cross-package interface and authority hold point; start BCAA/DoAT dependency tracking.
APMT
Week 2-3
5
试运行 IFC 发布门槛
Dry-run the 14-point issue checklist on a sample drawing set before the first contractual IFC freeze.
All leads
Week 3-4
STRICTLY CONFIDENTIAL
14