## Slide 1
TEAM ALIGNMENT
IFC Preparation
Airfield Package
Gelephu Airport (GLU) · Package 1 — Structuring the Issued-For-Construction set
APMT / PMO · Project Management Office
Airfield (P01) → Asset/Zone → Discipline/System → Document Type → Number → Revision/Status
STRICTLY CONFIDENTIAL
1

## Slide 2
Contents
This alignment covers scope, the IFC organising principle, the work-area matrix, controls, coding and the issue gate — for the Airfield package only
01
Scope & Principle
▸ Slide 3 — Scope of this IFC (Airfield)
▸ Slide 4 — Why align now
▸ Slide 5 — Organising principle
02
Structure & Controls
▸ Slide 6 — Airfield work-area matrix
▸ Slide 7 — Volume structure V0–V8
▸ Slide 8 — Master register
03
Coding & Interfaces
▸ Slide 9 — Key interfaces & hold points
▸ Slide 10 — Drawing coding
▸ Slide 11 — Specification coding
04
Gate, Roles & Next Steps
▸ Slide 12 — IFC issue checklist
▸ Slide 13 — Roles & lead ownership
▸ Slide 14 — Next steps
STRICTLY CONFIDENTIAL
2

## Slide 3
Scope of This IFC — Airfield Package
Package 1 (purple zone). The PTB & Landside package is a separate contract and is NOT part of this IFC
In Scope — Airfield Works (P01)
• Aircraft pavement — runway, taxiways, apron stands
• Airfield drainage, culverts & river-crossing works
• Earthworks & ground improvement
• Airfield Ground Lighting (AGL) & ALCMS
• Markings, signage & visual aids
• NAVAIDS / ANS (ILS, DME)
• Meteorological systems (MET)
• Integrated Building — ATCT, ARFF & MET
• Perimeter fencing, security & access gates
• Airside roads, car park & utilities
NSC / Specialist Equipment (subcontractors)
• AGL equipment
• NAVAIDS — ILS system equipment, DME, etc.
• ATCT special equipment
• Meteorological equipment
Interface to keep in view
Apron edge, PBB / AVDGS positions and stand services tie to the PTB & Landside package — coordinate the boundary even though those systems sit outside this IFC.
Boundary — PTB & Landside Package (separate contract, not in this IFC)
• PTB & PTB Annex · Canopy & Arrival Plaza · Ceremonial Lounge · landside roads, car park, landscape
• Terminal systems — BHS, HBS, PBB, AVDGS, PSS, FIDS, etc.
Remark: the list is not exhaustive — refer to the design for full details.
STRICTLY CONFIDENTIAL
3

## Slide 4
Why Align Now
The airfield is in tender / bid evaluation — a clean, controlled IFC set directly drives bid pricing, clarifications and claims exposure
1
Airfield is in tender / bid evaluation
IFC quality feeds bid pricing and risk premium directly. A controlled set reduces clarifications and EOT / claims exposure during evaluation, award and construction supervision.
2
BoQ gaps already flagged (~16 items)
ARFF vehicles, GSE, MET attribution, SFL units, CCTV / ICT active equipment, zero-quantity items, CAT I, etc. The IFC register must reconcile drawings, specifications and BoQ.
3
BCAA equipment compatibility unresolved
MET / ATC equipment specifications are not yet aligned with BCAA. Resolve, or clearly flag as pending clarification, before freezing the airfield IFC.
4
Aerodrome certification clock is running
BCAA certification takes ~2–3 years from design submission to operational approval. The airfield IFC feeds flight calibration and aerodrome certification — sequence accordingly.
5
One controlled register before first freeze
Avoid an uncontrolled airfield drawing list mixing pavement, AGL, NAVAIDS, MET, the integrated building and NSC equipment into one uncontrolled set.
6
Build on the existing PMO data room
Re-use WIP / Issued / Submission / Milestone Review folders and naming; add a stable IFC drawing number that does not change with the file name or issue date.
STRICTLY CONFIDENTIAL
4

## Slide 5
Organising Principle
The package is fixed (Airfield / P01). Organise everything below it by asset/zone, then discipline/system, then document type
Airfield
P01 — fixed
›
Asset / Zone
RWY · TWY · APR · DRN · IBG
›
Discipline /
System
CV · DR · AGL · NAV · MET · ST
›
Document
Type
Drawing · Spec · Schedule · Model
›
Number
Stable, date-independent
›
Revision /
Status
IFC · Superseded · As-Built
Worked example
GLU-P01-RWY-CV-PLN-0001 = Airfield · Runway · Civil · Plan · drawing 0001
Why it works: every airfield document resolves to a zone, discipline, type and revision — so pavement, AGL, NAVAIDS, MET, the integrated building and NSC equipment never collapse into one uncontrolled list. This keeps FIDIC administration, tender evaluation, award and claims management navigable.
STRICTLY CONFIDENTIAL
5

## Slide 6
Airfield Work-Area Matrix
Ten work areas inside Package 1 — each with its key works, primary disciplines, interfaces / hold points and owner
Work Area / Zone
Key Works & Disciplines
Key Interface / Hold Points
Owner
Runway, Taxiways & Apron
Aircraft pavement, geometry, markings, FOD, stands — CV / pavement
Apron–PBB/AVDGS (PTB pkg) · GSE · fuel · OLS / airspace
CAPE
Earthworks & Ground Improvement
Cut / fill, slopes, surcharge, ground treatment — geotech / CV
SI & ESIA · river training · schedule float
CAPE
Airfield Drainage & Culverts
Drainage, culverts, river-crossing works — DR / CV
ESIA & hydrology · landside outfall
CAPE
AGL, ALCMS & Visual Aids
Ground lighting, ALCMS, markings, signage — AGL / EL
Power supply · NAVAIDS · BCAA standards
CAPE / AGL spec.
NAVAIDS / ANS (ILS, DME)
Equipment siting, critical / sensitive areas — NAV
Airspace · DoAT · BCAA · flight calibration
NAVAIDS spec.
Meteorological Systems (MET)
AWOS, sensor siting, displays — MET
NCHM · BCAA · ATCT
MET spec. / NCHM
Integrated Building (ATCT/ARFF/MET)
Tower, ops rooms, ARFF station — AR/ST/ME/EL/ICT
ANS & MET equipment · power · water supply
CAPE / Aurecon
Perimeter, Security & Access
Fencing, gates, PIDS, patrol roads — SEC / CV / EL
Security ops · landside boundary
CAPE
Airside Roads, Car Park & Utilities
Service roads, car park, airside utilities — CV/ME/EL
Landside utilities tie-in
CAPE
NSC / Specialist Equipment
AGL eqpt · ILS / DME · ATC special · MET eqpt
FAT/SAT/T&C · BCAA compatibility · main-works interface
APMT / Spec.
STRICTLY CONFIDENTIAL
6

## Slide 7
Document Volume Structure
The same Volume 0–8 logic for the airfield package, so PM/CS teams and bidders navigate consistently
V0
IFC Master Register
One controlled register of every airfield drawing, spec, report, model & reference document in the baseline
V1
Governing / Contract Docs
Conditions of Contract · Particular Conditions · contract data · forms · clarifications & addenda
V2
Technical Specifications
Airfield specs by zone, discipline & system — pavement, drainage, AGL, NAVAIDS, MET, integrated building
V3
BoQ / Pricing Schedules
BoQ · rates · provisional sums · PC items · NSC pricing split · measurement rules
V4
Drawings
Airfield IFC drawings grouped by zone, discipline & drawing type
V5
Reports / Site Information
SI · geotech · hydrology · ESIA · survey · existing utilities — mark 'Contractual' vs 'For Info Only'
V6
Project / GMC / Authority
GMC · sustainability · OHS · BIM/CDE · local workforce · BCAA & aerodrome certification requirements
V7
BIM / Digital Deliverables
Airfield models · RVT/NWC/NWD/IFC · clash reports · model status · BEP · BIM QC · handover
V8
Interface & Authority Register
Interface matrix · BCAA / DoAT / NCHM tracker · RFI/TQ close-out · deviation register
STRICTLY CONFIDENTIAL
7

## Slide 8
Master Register
The core control matrix APMT maintains for the airfield package — the single source of truth for the IFC
Package Code
P01 Airfield (fixed)
Asset / Zone
Runway · Taxiway · Apron · Drainage · Earthworks · Integrated Building · ARFF · Perimeter
Discipline / System
CV DR AGL NAV MET ST AR ME EL SEC GEN BIM
Document Type
Drawing · Spec · Schedule · Report · Model · Calc
Document Number
Stable number — NOT dependent on date
Document Title
Full drawing or specification title
Revision
A/B/C · Rev 0/1 · IFC-A/IFC-B
Status
WIP · For Review · For Tender · IFC · Superseded · As-Built
IFC Baseline Date
Date included in the contractual IFC register
Originator
CAPE · AGL/NAV/MET specialists · Aurecon · survey
Checker / Approver
Designer checker · APMT reviewer · authority
Related Spec / BoQ
Cross-ref to spec section & BoQ item
Related Model
BIM model file name & revision
Authority Dependency
BCAA · DoAT · NCHM · BOC · Druk Air
Interface Dependency
Airfield–PTB · AGL–power · NAVAIDS–DoAT · MET–NCHM
Contractual Status
Contract Doc · Ref Only · CDP · Provisional Sum · NSC
Remarks / Open Items
Pending RFI · BoQ gap · BCAA compatibility · clarification
STRICTLY CONFIDENTIAL
8

## Slide 9
Key Interfaces & Hold Points
Cross-package and authority interfaces carry the most airfield IFC risk — log and track each one in the V8 register
Airfield ↔ PTB & Landside
Apron edge, PBB/AVDGS positions, stand services and apron–terminal levels must reconcile with the PTB package before either freezes.
Airspace / NAVAIDS ↔ DoAT
ILS / DME siting, critical & sensitive areas and OLS must be cleared with DoAT / ANSP — this gates flight calibration.
BCAA Equipment Compatibility
MET & ATC equipment specifications must be aligned with BCAA before the equipment / NSC scope is frozen.
Flight Calibration & Certification
IFC pavement, AGL, markings, NAVAIDS and MET feed BCAA aerodrome certification — sequence with the ~2–3 year clock.
Drainage / River-Crossing ↔ ESIA
Culverts and river-training works must align with ESIA mitigation and hydrology — exposure to authority oversight.
NSC / Specialist Equipment
AGL, ILS/DME, ATC special and MET equipment need power, containment, siting and FAT/SAT/T&C interfaces fixed with main works.
STRICTLY CONFIDENTIAL
9

## Slide 10
Drawing Coding
A stable drawing number that never changes with the file name or issue date — GLU-P01-[Asset]-[Discipline]-[Type]-[Sequence]
GLU - P01 - [Asset] - [Discipline] - [Type] - [Sequence]
Examples
GLU-P01-RWY-CV-PLN-0001
Runway · Civil · Plan
GLU-P01-RWY-CV-PRF-0005
Runway · Civil · Profile
GLU-P01-TWY-CV-PLN-0050
Taxiway · Civil · Plan
GLU-P01-APR-CV-LAY-0100
Apron · Civil · Stand layout
GLU-P01-APR-AGL-LAY-0120
Apron · AGL · Layout
GLU-P01-DRN-DR-PLN-0200
Drainage · Plan
GLU-P01-IBG-AR-PLN-0300
Integrated Building · Arch · Plan
GLU-P01-IBG-ME-SCH-0320
Integrated Building · Mech · Schedule
GLU-P01-NAV-SY-DIA-0400
NAVAIDS · System diagram
Discipline Codes
CV
Civil / Pavement
DR
Drainage
AGL
Airfield Ground Lighting
NAV
NAVAIDS / ANS
MET
Meteorological
ST
Structure
AR
Architecture
ME
Mechanical
EL
Electrical
FP
Fire Protection
ICT
ICT / ELV
SEC
Security / Fencing
LS
Landscape
GEN
General / Common
BIM
Digital Model
Asset / Zone codes: RWY Runway · TWY Taxiway · APR Apron · ERW Earthworks · DRN Drainage · IBG Integrated Building · ARF ARFF · PER Perimeter · RDS Airside Roads · UTL Utilities
STRICTLY CONFIDENTIAL
10

## Slide 11
Specification Coding
Use CSI MasterFormat as a reference, then add the airport-specific divisions — do not force airfield systems into building-only divisions
CSI MasterFormat (reference — incl. Integrated Building)
00
Procurement & contract
01
General · doc control · BIM/CDE · QA/QC · HSE
02
Existing conditions · clearance · utilities diversion
03
Concrete
05
Metals / structural / green steel
07
Roofing · waterproofing · façade
08
Doors · windows · glazing
09
Finishes
10
Signage · wayfinding · specialties
11
Airport & specialist equipment
21
Fire protection
22
Plumbing
23
HVAC
26
Electrical
27
Communications / ICT
28
Security / ELV / CCTV / access
31
Earthworks · ground improvement · slopes
32
Pavement · roads · external works
33
Utilities
Airport-specific — primary for this package
40-AF
Airfield civil works, geometry & pavements
41-AF
Airfield drainage, culverts, river-crossing
42-AF
Airfield markings, signage & visual aids
43-AF
Airfield Ground Lighting & ALCMS
44-AF
NAVAIDS, ANS & airspace infrastructure
45-AF
Meteorological systems
46-AF
ARFF facilities & fire training
48-OR
Testing, commissioning, ORAT, certification & handover
STRICTLY CONFIDENTIAL
11

## Slide 12
Minimum IFC Issue Checklist
Before any airfield drawing or specification is marked IFC, the team confirms each item — all are mandatory
✓
Included in the IFC master register
✓
Revision identified and frozen
✓
Design checker & approver complete
✓
APMT review complete
✓
Critical RFIs / TQs closed or pending-listed
✓
Related specification cross-referenced
✓
Related BoQ / pricing item cross-referenced
✓
BIM model revision aligned with drawing
✓
Interface with PTB & landside checked
✓
Authority dependency recorded (BCAA/DoAT/NCHM)
✓
NSC / specialist-equipment split identified
✓
Provisional sum / performance spec identified
✓
Marked 'Contract Document' or 'For Info Only'
✓
Superseded documents removed from baseline
STRICTLY CONFIDENTIAL
12

## Slide 13
Roles & Lead Ownership
Clear ownership inside the airfield package — APMT governs the register, interface matrix and the IFC issue gate
APMT / PMO
Overall airfield IFC governance · master register (V0) · interface & authority registers (V8) · IFC issue gate · BoQ reconciliation
P01 governance
CAPE
Airfield lead design — pavements, drainage, earthworks, AGL, markings, integrated building, perimeter & roads
P01 main works
AGL / Electrical Specialist
Airfield Ground Lighting, ALCMS and visual aids — design & equipment
AGL · ALCMS
NAVAIDS / ANS Specialist
ILS, DME and ANS siting, critical areas; coordination with DoAT
NAV / ANS
MET Specialist / NCHM
Meteorological systems siting & equipment; NCHM coordination
MET
QS / Cost
BoQ, schedules of rates, provisional sums and the NSC pricing split
V3 pricing
STRICTLY CONFIDENTIAL
13

## Slide 14
Next Steps
Kick off within two weeks of this alignment — master register and coding first, then reconcile drawings, specs and BoQ
1
Confirm organising principle & coding
Lock Airfield(P01)→Asset→Discipline→Type→Number→Rev; freeze drawing & specification coding (Slides 5/10/11).
All / APMT
Week 1
2
Stand up the Airfield IFC master register (V0)
Create the register with all 17 control fields; one register for P01, owned by APMT.
APMT / PMO
Week 1-2
3
Reconcile drawings ↔ specs ↔ BoQ
Close the ~16 BoQ gaps; map every drawing and specification to a BoQ item.
CAPE / QS
Week 2-3
4
Resolve BCAA compatibility & open V8 tracker
Align MET / ATC equipment specs with BCAA; start the BCAA / DoAT / NCHM dependency log.
APMT / Specialists
Week 2-3
5
Dry-run the IFC issue checklist
Test the 14-point gate on a sample airfield drawing set before the first contractual freeze.
All leads
Week 3-4
STRICTLY CONFIDENTIAL
14